2027

Method of Distribution

Community Development Block Grant (CDBG)

The Wyoming Community Development Authority (WCDA) is dedicated to community development throughout the State of Wyoming. This is accomplished using Community Development Block Grant (CDBG) funds from the US Department of Housing and Urban Development (HUD). In Title I of the Housing and Community Development Act of 1974, the CDBG program's primary goal is to develop viable communities by providing decent housing and suitable living environments and expanding economic opportunities, principally for persons of low and moderate incomes. The rules and regulations of the CDBG Program are regulated by the U.S. Department of Housing and Urban Development (HUD).

The Method of Distribution (MOD) is the guidance WCDA uses to allocate CDBG funds in support of community and neighborhood development projects in Wyoming communities. CDBG Application, Forms, Recipient Agreements, and Restrictive Deeds may be amended from time to time as guidelines and regulations are issued under 24 CFR Part 570, or as WCDA deems necessary. Unless otherwise stated, WCDA is entitled to the full discretion allowed by federal regulations and laws in making all such decisions and interpretations. WCDA may amend, disregard, modify, or withdraw any section of the MOD, including selection criteria with proper public notice.

WCDA distributes funds annually through a competitive statewide application process. All Wyoming non-entitlement units of general local government (UGLG) are eligible to apply for CDBG funding. This includes any city, county, town, or other general-purpose political subdivision of the State of Wyoming. Cheyenne is the only entitlement community in the State of Wyoming and cannot apply for State CDBG funding. Applications are scored and ranked against one another. Any funds remaining after the initial application process may be awarded through an additional competitive period once a formal announcement of funding availability has been made or will roll into the next annual funding cycle.

States participating in the CDBG Program have four major responsibilities that include:

- For the purpose of the program, WCDA is acting as HUD in its capacity

- Decide how to distribute funds among communities in non-entitlement areas

- Formulate community development objectives

- Ensure that recipients (local units of government) comply with state and federal laws and requirements

UGLG’s Participating in the CDBG Program has five major responsibilities that include:

- Evaluate environmental risk and act responsibly

- Consider the greatest community needs

- Prepare grant applications for submission to the State (WCDA)

- Carry out the funded community development activities

- Assume all risk as the Responsible Entity taking on the project

WCDA certifies that it will not refuse to distribute funds under this Method of Distribution to an applicant solely on the basis of a CDBG-eligible activity selected by the applicant for funding. However, WCDA has established a scoring system that may prioritize some activities over others.

National Objectives

Projects must meet at least one National Objective to be eligible for CDBG funding:

- Benefiting low and moderate-income persons primary national objective, no less than 75% of the total CDBG funds must be expended on projects that meet this objective.

- Preventing or eliminating slum or blight – Limited to addressing one or more conditions that contributed to the deterioration of a spot or area basis.

- Urgent Need (Applications can be accepted outside a competitive funding round).

Please note that CDBG defines moderate income as a household at or below 80% of Area Median Income (AMI), and low-income as at or below 50% of AMI. WCDA must show that at least seventy-five percent (75%) of its total CDBG funds, by activity, benefit low- to moderate-income persons.  Therefore, applicants applying under the remaining two National Objectives may not be funded if the statewide 75% minimum is not met.  Please refer to the WCDA CDBG Policy and Procedure Manual for more information regarding national objectives.

State of Wyoming Objectives

- Our goal is to help empower local governments and communities across the state by building the capacity, resiliency, and resource base necessary to develop strong, vibrant communities.

- Our goal focuses on benefiting low- to moderate-income people by providing resources for livable neighborhoods, economic empowerment, and decent housing in order to enhance the quality of life for low- and moderate-income residents, thereby strengthening Wyoming.

For technical assistance on any of the National or State Objectives please contact the WCDA CDBG staff.

Local Government Requirements: Citizen Participation

Every applicant and recipient of CDBG funds must comply with the citizen participation requirements provided in federal law and described in WCDA CDBG Policy & Procedure Manual.

Environmental Review

All HUD-assisted activities must have some level of environmental review completed. Compliance with 24 CFR Part 58 requirements is initiated with the submission of an application from the grantee for CDBG funds. Even exempt activities cannot be undertaken until a formal determination has been made. The environmental review aims to analyze the effect a proposed project will have on the people and the natural environment within a designated project area, and the effect the material and social environment may have on a project. Please refer to WCDA CDBG Policy & Procedure Manual for more information.

Application Requirements

- Completed Letter of Intent sent to neighborhooddev@wyomingcda.com on or before the submission deadline outlined in the respective Notice of Funding Availability (NOFA).

- After receipt of the Letter of Intent, WCDA will send applicants an email invite to ProCorem.

- Application with checklist and following supporting documents submitted to ProCorem by the deadline.

    - Certification of Applicant

    - Proof of Publication for citizen participation

    - All required documentation on the Environmental Tab, Specified in the Application

    - Photos minimum of 6 exterior, (if applicable minimum 6 interior)

    - Project budget: Third Party Cost Estimates (Minimum 2)

    - Risk Analysis of sub-recipient (when sub-granting)

    - Construction projects applicable environmental studies e.g., Phase I ESA

    - Rehab of a building built prior to 1978, Asbestos and Lead-Based Paint inspections.

    - Radon testing for any structure occupied more than four hours a day.

    - Signed Environmental Review Record Agreement

    - City Planning Documents & Strategic Plan if sub-granting

    - Reviewed Financial Statements (Minimum of most recent year)

    - Proof of System of Award Management (SAM) registration

    - Debarment Checks for applicant and subrecipient if applicable

    - Award/Commitment Letters of other funding

    - Market Analysis is required for any type of acquisition

    - Local Resolution

    - Deed, Easement of not less than 20 years, or similar formal executed documentation.

    - Conflict of Interest for applicant and subrecipient if applicable

    - WARM or LGP or Certificate of liability insurance certificate

    - Proof of procurement and contract for third party engineering services (if applicable)

WCDA does not have a funding cap, each UGLG is allowed to submit a maximum of two applications each funding cycle, and no more than two potentially open projects. WCDA will not consider an application if the UGLG has two open projects at the time of the application deadline.  WCDA will consider a project closed for application purpose, once WCDA has issued a final close out letter.

An UGLG may apply on behalf of a sub-recipient, housing developer, or business if they choose to do so. The UGLG is responsible for ensuring the sub-recipient complies with all applicable federal, state, and local laws, regulations, and ordinances. The UGLG is expected to conduct a risk analysis. It is recommended, but not required, that the UGLG develop written policies & procedures for monitoring a sub-recipient if they were to be awarded CDBG funds. Applicants will not be allowed to use any grant funds for administrative costs.

Applicants must be compliant with WCDA on any current project before an application will be accepted. After the application is received, WCDA will conduct a site visit to evaluate the site’s suitability for the proposed project. WCDA reserves the right to contact UGLG’s to clarify questions regarding their application. WCDA staff will be responsible for scoring and ranking the applications submitted.  The final review and award will be made by the WCDA Board of Directors. The award will be based on the project’s final ranking and the extent to which funds are available. It is possible that a project may rank and not receive funding.  At the time of application, all projects must demonstrate that adequate funding is available to complete the project and the project is ready to proceed. All projects involving the use of real property must include a deed, lease of not less than 20 years, easement, or similar formal executed documentation. If the project includes acquisition, a recent market analysis is required for the application, and if awarded a non-biased third-party appraisal will be required prior to funding.

The Wyoming Community Development Authority (WCDA) makes no representations herein as to compliance with the Housing and Community Development Act of 1974, 24 CFR Part 570, or any other laws or regulations governing the Community Development Block Grant (CDBG) Program. CDBG awards shall be made solely at the discretion of the WCDA Board of Directors, but in no way represents or warrants to any sponsor, investor, lender, or others that the project is, in fact, feasible or viable.  No board member, agent, or employee of WCDA shall be personally liable concerning any matters arising out of, or in relation to, the allocation of CDBG funds.

Applications may be rejected for any of the reasons listed in the WCDA Policy & Procedure Manual.

Project Evaluation and Scoring

All applications that meet the threshold criteria will be rated and ranked competitively by a review committee composed of WCDA staff with final approval of funds being determined by WCDA Board of Directors. Applicants will be given an opportunity to respond to questions in a timely manner.

*As long as there is no plan to use CDBG funding for a project’s design/planning, this will not trigger a choice-limiting action. Grantees will not be allowed to request that pre-award costs be reimbursed for these design/planning costs. If you plan to apply for CDBG funding for planning/design costs, please contact WCDA CDBG staff prior to entering any contracts.

Rating is based on a 150-point scale. Point ranges have been established for each criterion to gauge the extent to which the applicant meets the criterion. The following factors will be considered in determining the points assigned. Applicants will complete a self-scoring of the application as part of the application process.

| RANKING FACTOR | MAXIMUM POINTS |
| --- | --- |
| PUBLIC PURPOSE - Severity of Need (30) - Community Support (5) - Consistency (10) | 45 Points |
| PROJECT IMPACT - Affordability (0) or (5) - Impact on Need (10) or (5) - Benefit to LMI Households (10) | 25 Points |
| PROJECT MANAGEMENT - Readiness To Proceed (35) - Accuracy of Costs (10) - Administrative Capacity (10) | 55 Points |
| LOCAL COMMITMENT / LEVERAGING - Local Commitment (10) - Leveraging (15) | 25 Points |
| BONUS POINTS Total | 15 Points 150 Points |

### Public Purpose & Local Need (45 maximum points)

Severity of Need (30 maximum points). Points will be awarded based on low to moderate income (LMI) information provided in the application and information based on the level of distress or need.  The points for each section are outlined below.

- LMI

  - Ten (10) points For LMI areas or populations that have 60% or above.

  - Five (5) points For LMI areas or populations that have at least 51% to 59.99%.

  - Three (3) points For populations that are presumed LMI er HUD guidelines such as homeless, disabled, seniors, victims of domestic violence.

- Level of distress and/or need

  - Twenty (20) points Critical/Immediate (High Severity): Infrastructure in danger of imminent failure, posing direct threats to public health or safety, such as failed wastewater treatment, contaminated water supplies, or building falling down.

  - Fifteen (15) points Significant/High Deficiency: Major rehabilitation needed for critical facilities (water, sewer, roads) that are functioning below EPA or state standards.

  - Ten (10) points Moderate Deficiency: Improvements to existing infrastructure that are necessary for safety, such as upgrading storm drainage or installing sidewalks for pedestrian safety.

  - Five (5) points Replacement/Upgrading (Lower Severity): Projects focused on expanding capacity or modernizing infrastructure that is functional but aging.

Community Support and Involvement (5 maximum points). Points are awarded based on evidence and description of current community support and involvement in the project development and implementation. Letters of general support and participation may include local interest of neighborhood groups, local public or non-profit agencies and individuals that might directly benefit from the project. Applicants should describe the outreach conducted related to the public hearing and the efforts to obtain input from the public and those that might benefit directly from the project(s) included in the application. A minimum of 2 letters of support and detailed documentation of the outreach conducted in order to receive full points.

Consistency with Local Needs/Plans/Strategies (10 maximum points).

- Points are awarded based on the degree to which the project is specifically identified and is consistent with a locally developed revitalization strategy, capital improvements plan or comprehensive plan up to five (5) points. Relevant sections must be provided with the applications.

- Up to five (5) points may be awarded for proposed projects and activities that re-use existing buildings and infrastructure.

### Project Impact (25 maximum points)

Affordability (5 maximum points). Points are awarded based on total cost of project divided by intended beneficiaries. Five (5) points will be awarded for $0.00-$499.99. Four (4) points will be awarded for $500.00 -$999.99. Three (3) points will be awarded for $1,000.00-$1,999.99. Two (2) points will be awarded for $2,000.00-$2,999.99. One (1) points will be awarded for $3,000.00-$4,999.99. Zero (0) points will be awarded for $5,000.00 and above.

Impact on Need (10 maximum points). Points are awarded based on the extent to which the project will address the needs and alleviate the existing problems described by the applicant.

Benefit to Low and Moderate Income (LMI) Households (10 maximum points). Maximum points will be awarded to projects where there is a direct benefit to LMI households/persons. Five (5) points will be awarded to projects where there is an area wide benefit to LMI persons. No points will be given  for slum/blight projects where there is no benefit to LMI persons, or where benefit cannot be determined. If there is more than one national objective, maximum points will be given for the activity that benefits more people.

### Project Management (55 maximum points)

Readiness to Proceed (35 maximum points). Points may be awarded for the extent to which the project is ready to proceed, and the implementation schedule is reasonable. The assessment is based on the relative progress of elements such as site control/easements, architectural design or preliminary or final engineering, commitment of other project financing or the development of rehabilitation guidelines. This category considers the project as a whole but will consider factors such as phases as long as each phase is able to meet a national objective.

An applicant may receive thirty-five (35) points based on the following factors:

  - Construction Projects: Applicant has completed design and/or engineering, has completed acquisition or will complete if applicable within 90 days (does not include easement acquisition), can bid project within 90 days of executed agreement, and is able to start construction within 90 days of bid award.

  - Housing Rehabilitation Projects: Applicant has developed or updated all program materials, selected, and completed work write-ups for 30% of properties to be rehabilitated, and can bid work in 90 days of executed agreement.

  - Services/Non-Construction Projects: Applicant can demonstrate that program and/or activities can be implemented within 30 days of executed agreement.

An applicant may receive twenty (20) points based on the following factors:

- Construction Projects: Applicant has completed design and/or engineering, has completed acquisition or will complete if applicable within 120 days does not include easement acquisition, can bid project within 120 days of executed agreement, and is able to start construction within 120 days of bid award.

- Housing Rehabilitation Projects: Applicant has developed or updated all program materials, selected, and completed work write-ups for 15% of properties to be rehabilitated, and can bid work in 90 days of executed agreement.

- Services/Non-Construction Projects: Applicant can demonstrate that program and/or activities can be implemented within 60 days of executed agreement.

An applicant may receive ten (10) points based on the following factors:

- Construction Projects: Does not have design completed and Applicant will complete design and/or engineering within 120 days of executed agreement, will complete acquisition if applicable, within 120 days, and will bid project within 180 days of executed agreement.

- Housing Rehabilitation Projects: Applicant has developed or updated all program materials, selected, and completed work write-ups for 5% of properties to be rehabilitated, and can bid work in 120 days of executed agreement.

- Services/Non-Construction Projects: Applicant can demonstrate that program and/or activities can be implemented within 75 days of executed agreement

No points are awarded if the project is not ready to proceed based on the above criteria.

Accuracy of Costs (10 maximum points). Maximum points may be awarded to projects which best document that project costs have been carefully estimated. Estimates should reflect the applicability and impact of Davis-Bacon wage rates, acquisition requirements, relocation, or replacement housing requirements. Estimates should be current within six months. Preliminary professional studies, appraisals, tax assessments, wage rate determinations are some examples of acceptable documentation. A minimum of two cost estimates should be included with application. Application budget should be completed with each scope item. No points will be awarded if documentation of costs is not submitted.

Administrative Capacity (10 maximum points). Points may be awarded for projects based on the past performance of the applicant or subrecipient with CDBG grants (5 points maximum). WCDA will consider previous general grant management, financial management and compliance with meeting a national objective. The adequacy of staff to implement the proposed project based on information in previous grant administration of the application will also be considered (5 points maximum).

### Local Commitment and Leveraging (25 points maximum)

Local Commitment (10 maximum points). WCDA will consider the extent to which local funds will be contributed to the project. Maximum points (10) may be awarded to applicants whose local contribution equal to or exceeds 25% of the total project costs. Local contribution of 15%-24.99% of total project costs receives 8 points. Where there is some local contribution but less than 15% of the total project costs, 5 points are awarded. No points will be given where there is no local contribution. All funds must be adequately documented. Local funds include cash, debt service and any in-kind contributions which materially contribute to the project completion. In-kind contributions must be documented and may include the donation or long-term lease of land or buildings, appropriation of local revenues, site improvements or installed infrastructure, deferral of real estate taxes, abatement, or payment in lieu of taxes. The contribution may be provided by the local government or directly by subrecipient or business.

Leveraging (15 maximum points). WCDA will consider the extent to which local and CDBG funds are used to leverage other public and private funds (non-local). Points will be awarded based on the documented commitment of funds specifically identified to supplement CDBG funds. Maximum points fifteen (15) will be awarded for projects where 50% or more of the project costs are from sources other than local or CDBG. If 25% to 49.99% of the project costs are from sources of then local or CDBG ten (10) points will be awarded. If 15% to 24.99% of the project costs are from sources other than local or CDBG five (5) points will be awarded. If less than 15% of the project costs are from sources other than local or CDBG no points (0) will be awarded.

### Bonus Points (10 maximum points)

Applicants may receive up to 10 bonus points for meeting one or more of the following criteria if sufficiently discussed and/or documented within the application.  “Project activities” must directly relate to the CDBG funds being requested:

  - Project will use innovative materials or methods, include the replacement of utilities in existing buildings with energy saving materials and/or use green or energy efficient building materials and practices for new construction or renovation (2 Points);

  - Project activities include the acquisition and reuse of foreclosed or condemned properties (2 Points);

  - Project activities that directly benefit people experiencing homelessness (2 Points).

  - Project activities that directly benefit  those serving or have served in the U.S. armed forces (2 Points); or

  - Attend WCDA CDBG annual training (2)

### Funding Recommendations

The highest ranked applications are recommended for funding until the available funding for the round are exhausted or the next highest ranked project requests more funds than are available and the project cannot be phased. In that case, the next highest scoring project may be funded. In case of a tie score, the application with the highest combined score on Public Purpose & Local Need and Project Management is funded first. As noted at the beginning of this section, WCDA may consider other factors when making awards. In these cases, the other factors will be documented in the WCDA records.

### Performance Thresholds

There are performance thresholds related to previous CDBG grants that must be met by applicants. Applicants will be evaluated on their management of existing CDBG grants and must follow financial, reporting, monitoring, and performance requirements as established each year.

- Financial - Lack of expenditures and compliance with the CDBG Procurement Manual will be considered when new applications are ranked.

- Reporting – Applicants must be current with submission of any reports due to the program for existing grants.

- Monitoring – Grantees that have grants with open monitoring issues will be reviewed on a case- by-case basis, taking into consideration the significance of the finding(s) or concern(s), the corrective action(s) taken by the grantee or subrecipient to resolve the issue(s), and the timeliness of the grantee in responding.

- Performance – Grantees that have grants that have expended funds but have moved slowly or failed to perform in conformance with their project schedule. Grantees will be required to submit additional information related to reasons for delays and poor performance and a new timeline. WCDA reserves the right to determine if the response is sufficient.

In addition to the rating and evaluation criteria; WCDA staff and WCDA Board of Directors may consider other factors in making funding determinations, including:

•	WCDA’s objectives and priorities;

•	The availability of alternate or contributing funding sources for the total project or some of its components;

•	A reasonable distribution of projects among eligible regions of the State;

•	The ability to respond to a locality’s special needs;

•	The degree of community commitment for the project;

•	The previous CDBG investment in a community;

•	The ability of applicant, subrecipient or business to borrow funds;

•	The commitment and/or input from other funders;

•	The amount of CDBG funds awarded for other phases of a multi-phase project; and

•	The availability of other resources and/or services in a community.

- Environmental issues that cannot be mitigated or project site is located in a flood zone or floodplain.

- If a grantee returns competitively awarded funds without finishing project in its entirety, the grantee will

not be eligible for funding the next open cycle.

- In the event of funding oversubscription, where there are more qualified applicants than CDBG available

dollars, priority ranking will be given to non-water/sewer projects.

WCDA will provide final scores and general comments as to strengths and weaknesses of the UGLG application, if requested.

| Available Project Funding |  | Amount |
| --- | --- | --- |
| Community Development Block Grant (FY 26-27) |  |  |
| Community Development Block Grant (previous years) |  | $1,365,024.23 |
| Public Services |  | 15% Maximum per funding year |
| Slum and Blight |  | 25% Maximum per funding year |
| Urgent Need |  | 12% Maximum per funding year |
| Low to Moderate Income Persons Benefit |  | 75% Minimum |
| State Program Planning and State Administration |  | 3% Maximum |
| Application Cycle Timeline 2025-2026 |  |  |
| Task | Deadline |  |
| Notice of Funding Availability | June 2026 |  |
| Letter of Intent | August 31st 2026 |  |
| Application Submittal | September 30th 2026 |  |
| WCDA Board Funding Approval | January 2027 |  |

Contact Information

General CDBG email

Neighborhooddev@wyomingcda.com

Kaycee Hurless

Neighborhood Development Officer

Wyoming Community Development Authority

hurless@wyomingcda.com

307.233.0031 (Office)

307.277.1605 (Cell)

307.266.5414 (Fax)

Lorie Ordiway

Neighborhood Project Specialist I

Wyoming Community Development Authority

ordiway@wyomingcda.com

307.233.0029 (Office)

307.266.5414 (Fax)

Tammy Brandt

Director of Housing & Neighborhood Development

Wyoming Community Development Authority

brandt@wyomingcda.com

307.233.0051 (Office)

307.262.4563 (Cell)

307.266.5414 (Fax)